## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Database Application for Hotel Manoir Ramezay | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | RED TEAM - Systems Development Project | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Patrick Larocque / Chi-Tao Li / Murat Osmonov / Gerasimos (Gerry) Vlassopoulos / Li Yu | Project Start: |  | 2022-09-07
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-09-05 to 2022-11-13
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-09-05 to 2022-11-13
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Deliverable 1.0 - Project Plan (Team Leader: Patrick) |  |  | 2022-02-09 | 2022-09-16 | 220 | bar: 2022-09-05 to 2022-09-16
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 1.1 - Cover Page (10 marks) | Gerry / Patrick | 50% | 2022-02-09 | 2022-09-10 | 214
| *Must include signature certification underneath | Patrick
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 1.2 - List of previous work used (2 marks) | Patrick / Chi-Tao / Gerry | 50% | 2022-02-09 | 2022-09-10 | 214
| 1.3 - Table of contents (2 marks) | Patrick | 50% | 2022-02-09 | 2022-09-10 | 214
| 1.4 - One Page Executive Overview (5 marks) | Li Yu + Everyone | 0% | 2022-02-09 | 2022-09-12 | 216
| 1.5 - Identified Potential and Chosen Client/Sponsor (10 marks) | Patrick / Gerry / Chi-Tao / Li Yu | 25% | 2022-02-09 | 2022-09-12 | 216
Brief Description of client
Computer skills and literacy for the client
Statement/Description of the Business Problem to be solved
| 1.6 - Team description division workload (22 marks) | Patrick + Everyone | 50% | 2022-02-09 | 2022-09-12 | 216
Team Meeting Agenda
Online repositories
Communication Strategies
Meeting schedule
Areas of responsibility
Contacts of information
| 1.7 - Gantt Chart design and project plan (11 marks) | Chi-Tao | 15% | 2022-02-09 | 2022-11-09 | 274
| 1.8 - Ensuring correct spelling & grammar (3 marks) | Patrick / Chi-Tao | 15% | 2022-09-16 | 2022-09-16 | 1
| 1.9 - Ensuring a well-formatted report (3 marks) | Patrick + Everyone | 15% | 2022-09-16 | 2022-09-16
| 1.10 - Submitting report in PDF format (1 mark) | Patrick | 15% | 2022-09-16 | 2022-09-16
| 1.11 - Team Leader Presentation | Patrick | 0% | 2022-09-19 | 2022-09-19
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Deliverable 2.0 - Client and Business Domain summaries and questionaires (Team Leader: Li Yu)
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 2.1 - Including existing Cover Page + table of content (3 marks) | Li Yu | 0% | 2022-09-23 | 2022-09-23 | 1
| *Must include signature certification underneath | Li Yu
| 2.2 - Executive Overview (5 marks) | TBD | 0% | 2022-09-16 | 2022-09-23 | 8
| 2.3 - Business Domain Description (5 marks) | TBD | 0% | 2022-09-16 | 2022-09-23 | 8
| 2.4 - Business Environment Description (5 marks) | TBD | 0% | 2022-09-16 | 2022-09-23 | 8
| 2.5 - Client Description (3 marks) | TBD | 0% | 2022-09-16 | 2022-09-23 | 8
| 2.6 - Business Problem (5 marks) | TBD | 0% | 2022-09-16 | 2022-09-23
| 2.7 - Exploring open questions (10 marks) | Exeryone | 0% | 2022-09-16 | 2022-09-23 | 8
| 2.8 - Questionaire (10 marks) | TBD | 0% | 2022-09-16 | 2022-09-23
| 2.9 - Proper use of References (2 marks) | TBD | 0% | 2022-09-16 | 2022-09-23
| 2.10 - Bibliography / APA format (2 marks) | TBD | 0% | 2022-09-23 | 2022-09-23
| 2.11 - Ensuring correct spelling, grammar and formatting (3 marks) | Patrick / Chi-Tao | 0% | 2022-09-23 | 2022-09-23
| *Submitting report in PDF format | Li Yu | 0% | 2022-09-23 | 2022-09-23
| 2.12 - Team Leader Presentation | Li Yu | 0% | 2022-09-26 | 2022-09-26
Sample phase title block | Deliverable 3.0 - Analysis: Use cases and UML Diagrams (Team Leader: Gerrasimos (Gerry) )
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 3.1 - Including existing Cover Page + table of content (3 marks) | Gerry | 0% | 2022-09-23 | 2022-09-30 | 8
| *Must include signature certification underneath | Gerry
| 3.2 - Executive Overview (5 marks) | TBD | 0% | 2022-09-23 | 2022-09-30 | 8
| 3.3 - Summary Client Description (3 marks) | TBD | 0% | 2022-09-23 | 2022-09-30 | 8
| 3.4 - Business Problem Descriiption (5 marks) | TBD | 0% | 2022-09-23 | 2022-09-30 | 8
| 3.5 - Narrative Description of the present info system (10 marks) | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.6 - Appendix 1: Use cases (5 marks) | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.7 - Appendix 2: Two representatives of use cases found in the system diagram (8 marks) | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.8 - Appendix 3: Two representatives of UML Diagram | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.9 - Appendix 4: Class Diagram for the entire existing info system | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.10 - Appendix 5: State Chart Diagram for a significant class | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.11 - Appendix 6: Copies of forms and other documental used by client | TBD | 0% | 2022-09-23 | 2022-09-30
| 3.12 - References, Bibliography and Work Cited (APA format) | TBD | 0% | 2022-09-30 | 2022-09-30
| 3.13 - Ensuring spelling, grammar and formatting | Patrick / Chi-Tao | 0% | 2022-09-30 | 2022-09-30 | 1
| * Submitting report in PDF format | Gerry | 0% | 2022-09-30 | 2022-09-30 | 1
| 3.14 - Team Leader Presentation | Gerry | 0% | 2022-10-05 | 2022-10-05 | 1
Sample phase title block | Deliverable 4.0 - Requirements: User Stories (Team Leader: Murat)
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 4.1 - Including existing Cover Page + table of content (3 marks) | Murat | 0% | 2022-09-30 | 2022-10-14 | 15
| *Must include signature certification underneath | Murat
| 4.2 - Executive Overview (4 marks) | TBD | 0% | 2022-09-30 | 2022-10-14 | 15
| 4.3 - Revised Summary Client Description (3 marks) | TBD | 0% | 2022-09-30 | 2022-10-14 | 15
| 4.4 - Business Problem (5 marks) | TBD | 0% | 2022-09-30 | 2022-10-14 | 15
| 4.5 - Narrative Description of the future info system (10 marks) | TBD | 0% | 2022-09-30 | 2022-10-14 | 15
| 4.6 - Appendix 1 - Process used for user stories, List of user stories; and Product Backlog (10 marks) | TBD | 0% | 2022-09-30 | 2022-10-14
| 4.7 - Appendix 2 - Chosen user stories (at least two), and transcriptions of all user story tests (5 marks) | TBD | 0% | 2022-09-30 | 2022-10-14
| 4.8 - Appendix 3 - User story map (choice of tools used, story map printout, and references for the user stories) (10 marks) | TBD | 0% | 2022-09-30 | 2022-10-14
| 4.9 - References / Bibliography / Work Cites (APA format) (2 marks) | TBD | 0% | 2022-10-14 | 2022-10-14
| 4.10 - Ensuring correct spelling, grammar and formatting (3 marks) | Patrick / Chi-Tao | 0% | 2022-10-14 | 2022-10-14
| * Submitting report in PDF format | Murat | 0% | 2022-10-14 | 2022-10-14
| 4.11 - Team Leader Presentation | Murat | 0% | 2022-10-17 | 2022-10-17
Deliverable 5.0 - Prototype User Interface and Initial Client Comments (Team Leader: Chi-Tao)
| 5.1 - Including existing Cover Page + table of content (3 marks) | Chi-Tao | 0% | 2022-10-14 | 2022-10-24
| *Must include signature certification underneath | Chi-Tao
| 5.2 - Executive Overview (4 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.3 - Revision summary of project's narractive description (5 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.4 - Buisness Problem (4 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.5 - List of usability guidelines (at least 10) with brief explainations, sources for each guideline and references (10 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.6 - Copies of the prototype interface developped (at least 5 screens in this prototypes) (10 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.7 - Client comments and interactions (19 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
Process description used
Clients comment of hand-drawn prototype
Client comments on computer-drawn protype
| 5.8 - Description of the progression and changes in the prototype (10 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.9 - Appendix 1: Revised User stories and tests (5 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.10 - Appendix 2: Revised story maps (5 marks) | TBD | 0% | 2022-10-14 | 2022-10-24
| 5.11 - References / Bibliography / Work Citred (APA format) (2 marks) | TBD | 0% | 2022-10-24 | 2022-10-24
| 5.12 - Ensuring correct spelling, grammar and formatting (3 marks) | Patrick / Chi-Tao | 0% | 2022-10-24 | 2022-10-24
| * Submitting report in PDF format | Chi-Tao | 0% | 2022-10-24 | 2022-10-24
| 5.13 - Team Leader Presentation | Chi-Tao | 0% | 2022-10-26 | 2022-10-26
Deliverable 6.0 - Database Design (Team Leader: Li Yu)
| 6.1 - Including existing Cover Page + table of content (3 marks) | Li Yu | 0% | 2022-10-24 | 2022-10-31
| *Must include signature certification underneath | Li Yu
| 6.2 - Executive Overview (4 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.3 - Buisness Problem (3 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.4 - Narrative Desription of Database Design (10 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.5 - Block Diagram (5 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.6 - Appendix 1: Data Dictionary (10 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.7 - Appendix 2: ER Diagram, including comparisons from other diagrams from various appendix (15 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.8 - Appendix 3: Description/explanations of the Indexes & Database architecture; and the Design's query optimization (4 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.9 - Appendix 4: Projected size of database (9 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.10 - Appendix 5: Required acess speed data (5 marks) | TBD | 0% | 2022-10-24 | 2022-10-31
| 6.11 - References / Bibliography / Work Citred (APA format) (2 marks) | TBD | 0% | 2022-10-31 | 2022-10-31
| 6.12 - Ensuring correct spelling, grammar and formatting (3 marks) | Patrick / Chi-Tao | 0% | 2022-10-31 | 2022-10-31
| * Submitting report in PDF format | Li Yu | 0% | 2022-10-31 | 2022-10-31
| 6.13 - Team Leader Presentation | Li Yu | 0% | 2022-11-02 | 2022-11-02
Deliverable 7.0 - Implementation and Final Client Comments (Team Leader: Patrick)
| 7.1 - Including existing Cover Page + table of content (3 marks) | Patrick | 0% | 2022-10-31 | 2022-11-09
| *Must include signature certification underneath | Patrick
| 7.2 - Executive Overview (4 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.3 - Summary Client Description FINAL (5 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.4 - Revised summary narrative description of the system (3 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.5 - Client comments (5 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.6 - Discussions (5 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.7 - Description of current security measure (5 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.8 - Future Work (16 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
User Interface improvements
Unimplemented user stories and functions
Reccomendations regarding future security measures to be taken
Reccomendations regarding unit and integration test strategies to be used
An Acceptance Test Plan
| 7.9 - Appendix 1: Revised User Interface (5 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.10 - Appendix 2: Printed version of the User Guide (10 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.11 - Appendix 3: Interface screen images and lists (10 marks) | TBD | 0% | 2022-10-31 | 2022-11-09
| 7.12 - References / Bibliography / Work Citred (APA format) (2 marks) | TBD | 0% | 2022-11-09 | 2022-11-09
| 7.13 - Ensuring correct spelling, grammar and formatting (3 marks) | Patrick / Chi-Tao | 0% | 2022-11-09 | 2022-11-09
| *Submitting report in PDF format | Patrick | 0% | 2022-11-09 | 2022-11-09
| 7.14 - Team Leader Presentation | Patrick | 0% | 2022-11-09 | 2022-11-09
Miscallaneous
| Team Logbook |  |  | 2022-09-02 | 2022-11-04
| *Logbook #1 | Everyone | 0% | 2022-09-02 | 2022-09-14
| *Logbook #2 | Everyone | 0% | 2022-09-14 | 2022-09-28
| *Logbook #3 | Everyone | 0% | 2022-09-28 | 2022-10-12
| *Logbook #4 | Everyone | 0% | 2022-10-12 | 2022-11-04
| TEAM Learning Integration Assessment |  |  | 2022-09-02 | 2022-11-09
| *LIA Prototype | Everyone | 0% | 2022-11-09 | 2022-11-09
| TEAM Demonstration | Everyone | 0% | 2022-11-11 | 2022-11-11